## SDBIP 2025-2026
FINANCE DEPARTMENT SDBIP 2026-2027
No | OBJECTIVE | STRATEGY | IDP/INDICATOR NO | KEY PERFORMANCE INDICATOR/UNIT OF MEASURE | BASELINE / BACKLOG | ANNUAL TARGET | WEIGHT | AUDIT EVIDENCE REQUIREMENT | BUDGET | QUARTER 1 ENDING 30 SEP | QUARTER 2 ENDING 31 DEC | QUARTER 3 ENDING 31 MAR | QUARTER 4 ENDING 30 JUN
[10 empty] | TARGET | TARGET | TARGET | TARGET
KPA: MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
PERFORMANCE MANAGEMENT AND REPORTING
1 | To manage and enhance the performance of the municipality by compiling and submission of monthly and quarterly reports | Signing of Individual Performance Agreements and quarterly assessement/reviews | MTID 1/FS/25/27 | a) Number of Individual Performance Agreements and Work Plans signed b) Number of quarterly performance assessment/reviews conducted | 20 | a) 20 Individual Performance Agreements b) 4 Quarterly Assessment / Reviews conducted for 19 employees by 30 June 2027 |  | a.) Signed Individual performance agreements and work plans b.) Signed Quarterly assessment/ review forms | N/A | a) 20 Performance agreements signed by 30 July 2026 b) Conduct quarterly assessments/reviews for 19 employees | a) Conduct quarterly assessments/reviews for 20 employees | Conduct quarterly assessments/reviews for 20 employees | a) Conduct quarterly assessments/reviews for 20 employees
2 |  | Compiling and submission of monthly and quarterly reports | MTID 2/FS/26/27 | Number of Monthly Performance Reports compiled | 8 | 8 Monthly Performance Reports compiled by 30 June 2027 |  | Signed off Monthly Performance reports by 30 June 2027 | N/A | July and August monthly reports | Oct and Nov monthly reports | Jan and Feb monthly reports | Apr and May monthly reports
3 |  |  | MTID 3/FS/26/27 | Number of signed off Quarterly SDBIP reports submitted to the portfolio within 30 days of the last day of each quarter. | 4 | 4 signed off Quarterly SDBIP reports submitted to the portfolio within 30 days of the last day of each quarter. |  | a) Copy of signed off SDBIP quarterly report b) Copy of portfolio recommendation/resolution | N/A | Quarter 4 report by 30 July 2026 | Quarter 1 report by 30 Oct by 2026 | Quarter 2 report by 30 Jan 2027 | Quarter 3 report by 30 Apr 2027
4 |  |  | MTID 4/FS/26/27 | a) Number of monthly performance reports and POEs submitted to PMS unit on due date b) Number of quarterly reports and POEs submitted to PMS unit on due date | 8 | a) 8 monthly performance reports and POEs submitted to PMS unit on due date b) 4 quarterly performance reports and POEs submitted to PMS unit on due date |  | a) Proof of submission b) Signed Quarterly POE verification form | N/A | a) Submit monthly reports and POEs to PMS unit within 10 working days after the end of the month (July and August monthly reports) b) Submit quarterly report and POEs to PMS unit within 10 working days after the end of the quarter (Q4 report) | a) Submit monthly reports and POEs to PMS unit within 10 working days after the end of the month (Oct and Nov monthly reports) b) Submit quarterly report and POEs to PMS unit within 10 working days after the end of the quarter (Q1 report) | a) Submit monthly reports and POEs to PMS unit within 10 working days after the end of the month (Jan and Feb monthly reports) b) Submit quarterly report and POEs to PMS unit within 10 working days after the end of the quarter (Q2 report) | a) Submit monthly reports and POEs to PMS unit within 10 working days after the end of the month (April and May monthly reports) b) Submit quarterly report and POEs to PMS unit within 10 working days after the end of the quarter (Q3 report)
Total Weighting
MEETINGS
5 | Strengthen institutional governance, coordination and administrative efficiency within the municipality. | Conduct regular BTO staff meetings to monitor departmental performance, improve communication, coordinate activities, and ensure implementation of Council and management resolutions. | MTID 5/FS/26/27 | Number of Monthly Community Services departmental meetings held | 12 | 12 Departmental meetings held by 30 June 2027 |  | a) Minutes b) Attendance registers | N/A | 3 | 3 | 3 | 3
6 | To ensure effective governance through regular meeting of Council structures | Coordinate and facilitate Section 79 Committee meetings to ensure effective oversight of departmental programmes, policies, and performance. | MTID 6/FS/26/27 | Number of Portfolio committee meetings held | 12 | 12 Portfolio committee meetings held by 30 June 2027 | 2% | a) Portfolio minutes b) Attendance registers | N/A | Hold 3 Portfolio committee meetings | Hold 3 Portfolio committee meetings | Hold 3 Portfolio committee meetings | Hold 3 Portfolio committee meetings
Total Weighting
KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Audit findings and Risk Management
7 | Strengthen governance, accountability, risk management, and internal controls within the municipality. | Monitor the implementation of Internal Audit and AG recommendations and ensure timely resolution of audit findings. | GGPP 1/FS/26/27 | Percentage of Internal Audit Findings resolved on quarterly and annual basis | 100% | 100% of quarterly and annual Internal Audit findings resolved within 30 June 2027 |  | (a) Internal audit action plan (Q1-Q4) b) Executive summary report on achievements by Internal Audit Manager (Q1-Q4) c) Final Annual audit findings status report | N/A | a) 100% Resolution of Internal Audit findings due in Quarter 4 (2025/2026) | a) 100% Resolution of Internal Audit findings due quarter 1 | a) 100% Resolution of Internal Audit findings due in Quarter 2 | a) 100% Resolution of Internal Audit findings due in Quarter 3
8 |  |  | GGPP 2/FS/26/27 | Percentage of AG Audit Findings resolved on quarterly and annual basis | 100% | 100% of quarterly and annual AG Audit findings resolved within 30 June 2027 |  | a) AG action plan and Council resolution (Q1) b) Executive summary report on achievements by Internal Audit Manager (Q1-Q4) c) Final Audit Action Plan report, Internal Audit report | N/A | N/A | N/A | a) Develop AG action plan and table to council b) 30% resolion of AG findings in quarter 3 | a) 100% resolution of AG findings
9 | Improve audit performance and strengthen sustainable internal controls. | Address root causes of audit findings and implement corrective measures to prevent recurrence. | GGPP 2/FS/26/27 | Number of repeat AG audit findings | NEW | 0 AG repeat audit findings |  | a) Auditor-General Management Report b) Annual Report on Audit Outcomes c) Executive summary report on achievements by Internal Audit Manager |  | N/A | N/A | 0 repeat AG audit findings | N/A
10 |  |  | GGPP 3/FS/26/27 | Number of repeat internal audit findings. | NEW | 0 repeat internal audit findings |  | a) Internal Audit Reports b) Executive summary report by Internal Audit Manager (Q1-Q4) |  | N/A | 0 | 0 | 0
11 | Promote community participation and stakeholder engagement in municipal planning and budgeting processes. | Facilitate public consultation meetings on the Integrated Development Plan (IDP) and Municipal Budget in accordance with legislative requirements and the approved public participation programme. | GGPP 4/FS/26/27 | Number of IDP/ Budget public consultation meetings held | 4 | a) 4 IDP/Budget public consultation meetings held by 31 May 2027 |  | Reports and attendance registers | 837000 | N/A | N/A | N/A | 4 IDP/Budget public consultations meetings held by 31 May 2027
Enterprise Risk management
12 | To bring the organization to an enabled risk maturity level | Mitigating risks identified in the risk register | GGPP 5/FS/26/27 | Percentage completion of Action Plans relevant to FIMS for each quarter as documented in the operational risk register | 100% | 100% completion of Action Plans relevant to FIMS per quarter up to 30 June 2027 |  | a.) Updated risk register and Action Plan b.) Sign-off document as proof of endorsement by CFO c.) Executive summary report on achievements by Risk Manager | N/A | 100% completion of risk action plans due in (Q1) | 100% completion of risk action plans due in (Q2) | 100% completion of risk action plans due in (Q3) | 100% completion of risk action plans due in (Q4)
13 | Strengthen governance, accountability, and monitoring of Council decisions. | Maintain and update the Council Resolution Register to track resolutions and facilitate implementation monitoring. | GGPP 6/FS/26/27 | a) Number of updates of the Council Resolution Register. b) Percentage of Council resolutions implemented. | a) 4 b) 100% | a) 4 updates of council resolution register by 30 June 2027 b) 100% implementation of BTO resolutions by 30 June 2027 |  | a) Updated council resolution register b) Report on implementation of council resolutions (Q4) | N/A | 1 updated council resolution register | 1 updated council resolution register | 1 updated council resolution register | a) 1 updated council resolution register b) 100% implementation of Council resolutions
Total Weighting
KPA: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Expenditure: Budget and Reporting
14 | Compliance with financial legislation and policies | Facilitate the preparation, consultation, and submission of the annual budget for Council approval within the legislative timeframe prescribed by Section 24(1) of the MFMA. | MFVM 1/FS/26/27 (IDP/TL) | 2027/2028 Budget approved by Council in terms of Section 24(1) of the MFMA. | 2026-05-31 | 2027/2028 Budget approved by Council in terms of Section 24(1) of the MFMA by 31 May 2027 |  | a) 2027/2028 IDP/Budget Process plan and Council resolution (Q1) b) 2027/2028 Draft budget and council resolution (Q3) c) 2027/2028 Final budget and council resolution (Q4) | N/A | Table 2027/2028 IDP/Budget Process plan to council by 31 Aug 2026 | N/A | Table 2027/2028 Draft budget to Council for approval by 31 March 2027 | Table 2027/2028 Final budget to Council for approval by 31 May 2027
15 |  | Prepare, consult on, and obtain Council approval for a credible, funded, and legislatively compliant 2027/2028 budget within prescribed timeframes. | MFVM 2/FS/26/27 (IDP/TL) | 2027/2028 funded budget approved by Council within legislated timeframes. | 2026-05-31 | 2027/2028 funded budget approved by Council by 31 May 2027 |  | a) Draft operating and capital budget projections (Q2) b) Engagement with depts on budget submissions (communication-Q2) b) 1 funded budget approved by 31 May 2027 |  | N/A | Develop draft operating and capital budget projections; engage departments on budget submissions. | N/A | Final 2027/2028 funded budget approved by Council.
16 |  | Conduct a Mid-Year Budget and Performance Assessment and submit the required report in accordance with Section 72 of the MFMA. | MFVM 3/FS/26/27 (IDP/TL) | 2026/2027 Mid-Year Budget and Performance Assessment conducted and approved in terms of Section 72 of the MFMA. | 2026-01-25 | 2026/2027 Mid-Year Budget and Performance Assessment completed and submitted to council in terms of Section 72 by 25 January 2027 |  | a) 2026/2026 mid-year financial review report b) Council resolution | N/A | N/A | N/A | Table 2026/2027 Mid-Year Budget and Performance Assessment to council by 25 Jan 2027 | N/A
17 |  | Prepare and submit an Adjustment Budget for Council consideration and approval in accordance with Section 28 of the MFMA. | MFVM 4/FS/26/27 (IDP/TL) | Adjustment Budget approved in terms of Section 28 of the MFMA. (Legislated date) | 2026-02-28 | 2026/2027 Adjustment Budget tabled and approved by Council in terms of Section 28 of the MFMA by 28 February 2027 |  | a) Approved 2026/2027 Adjustment Budget b) Council resolution | N/A | N/A | N/A | Table2026/2027 Adjustment budget to council by 28 February 2027 | N/A
18 |  | Investigate, monitor, and report all instances of Unauthorized, Irregular, Fruitless and Wasteful Expenditure (UIFW) and table reports to Council in accordance with legislative requirements. | MFVM 5/FS/26/27 (IDP/TL) | Number of Unauthorized, Irregular or fruitless and wasteful expenditure Reports tabled to council | 4 | 4 Unauthorized, Irregular or fruitless and wasteful expenditure Reports tabled to council by 30 June 2027 |  | a) Annual UIFW report, register and council resolution (Q1) b) UIFW expenditure register and council resolutions (Q2-Q4) | N/A | 1 UIFW expenditure report tabled to Council (2025/2026 UIFW) | 1 UIFW expenditure report tabled to Council (Q1 UIFW) | 1 UIFW expenditure report tabled to Council (Q2 UIFW) | 1 UIFW expenditure report tabled to Council (Q3 UIFW)
19 |  | Eliminate and prevent Unauthorised, Irregular, Fruitless and Wasteful (UIFW) expenditure through effective controls, monitoring, and consequence management. | MFVM 6/FS/26/27 (IDP/TL) | Percentage reduction in UIFW expenditure compared to prior year. | NEW | 95% elimination of 2025/2026 UIFW expenditure by 30 June 2027. |  | Auditor-General audit report | N/A | Develop UIFW Strategy | N/A | N/A | 95% (2025/2026 UIFW)
20 |  | Monitor and report on the implementation of the approved Procurement Plan and table quarterly progress reports to Council for oversight and accountability. | MFVM 7/FS/26/27 (IDP/TL) | Number of quarterly reports on implementation of the Procurement Plan tabled to Council. | 4 | 4 Quarterly Procurement Plan Implementation Reports tabled to Council by 30 June 2027 |  | a) Procurement Plan implementation reports b) Council resolutions | N/A | 1 Procurement Plan implementation report tabled to Council | 1 Procurement Plan implementation report tabled to Council | 1 Procurement Plan implementation report tabled to Council | 1 Procurement Plan implementation report tabled to Council
21 |  | Prepare and submit monthly budget statements to the Mayor within the prescribed timeframe in accordance with Section 71 of the MFMA. | MFVM 8/FS/26/27 | Number of monthly financial reports submitted to the Mayor within 10 working days after month end in terms of S.71 of the MFMA. | 12 | 12 monthly financial reports submitted to the Mayor within 10 working days after month end in terms of S.71 of the MFMA by 30 June 2027 |  | a) Section 71 reports b) Copy of the resolutions taken by Finance Portfolio Committee in respect of the reports submitted. | N/A | 3 monthly financial reports submitted within 10 working days to Finance portfolio Committee (Jun,Jul, Aug) | 3 monthly financial reports submitted within 10 working days to Finance portfolio Committee (Sept, Oct, Nov) | 3 monthly financial reports submitted within 10 working days to Finance portfolio Committee (Dec, Jan, Feb) | 3 monthly financial reports submitted within 10 working days to Finance portfolio Committee (Mae Apri, May)
22 |  | Prepare and submit quarterly financial and implementation reports to Council within 30 days after the end of each quarter in accordance with Section 52(d) of the MFMA. | MFVM 9/FS/26/27 (IDP/TL) | Number of quarterly financial reports submitted to council within 30 days of the end of each quarter in terms of S.52 of the MFMA. | 4 | 4 quarterly financial reports submitted to council within 30 days of the end of each quarter in terms of S.52 of the MFMA by 30 June 2027 |  | a) Sec 52 Quarterly reports b) Council resolutions | N/A | Sec 52 Financial Report (2025/2026 Q4 report) | Sec 52 Financial Report (Q1) | Sec 52 Financial Report (Q2) | Sec 52 Financial Report (Q3)
23 |  | Prepare, obtain Council approval where applicable, and submit the Annual Financial Statements (AFS) to the Auditor-General within the legislated timeframe. | MFVM 10/FS/26/27 (IDP/TL) | 2025/2026 Council-approved Annual Financial Statements submitted to the Auditor-General by 31 August 2026. | 2026-08-31 | 2025/2026 Annual Financial Statements submitted to the Auditor-General by 31 August 2026 |  | a) Annual Financial Statements (Q1) b) Council resolution (Q1) c) Proof of submission/Acknowledgement of receipt (Q1) d) AFS preparation plan, year-end closure plan (Q4) | N/A | Submit 2025/2026 AFS to to AG by 31 Aug 2026 | N/A | Preparation for 2027/2028 year-end financial reporting initiated | N/A
24 |  | Prepare and submit the 2025/26 Annual Financial Statements (AFS) to Council for consideration and noting within prescribed timelines and Prepare and submit interim financial statements to the Finance Portfolio Committee for monitoring, accountability, and corrective action. | MFVM 11/FS/26/27 (IDP/TL) | a) 2025/26 Annual Financial Statements tabled to Council. b) Number of 2026/27 Interim Financial Statements tabled to the Finance Portfolio Committee. | a) 31 August b) 2 | a) 2025/26 AFS tabled to council for adoption by 31 Aug 2026 b) 2 2026/27 Interim Financial Statements tabled to Finance Portfolio Committee by 30 June 2027 |  | a) 2025/26 Annual Financial Statements and council resolution b) Interim Financial Statements c) Finance Portfolio Committee recommendations/Resolutions | N/A | Table of 2025/26 AFS to Council by 31 August 2026 | N/A | 2026/27 1st Interim Financial Statements tabled to Finance Portfolio Committee | 2026/27 2nd Interim Financial Statements tabled to Finance Portfolio Committee
25 |  | Pay all creditors within 30 days after receipt of invoice | MFVM 12/FS/26/27 | Percentage of payment of all creditors within 30 days after receipt of invoice | 100% | 100% payment of creditors within 30 days after receipt of invoice per quarter up to 30 June 2027 |  | (a) Copy of creditors age analysis (b) Register of invoices | N/A | 100% creditors paid <30 days | 100% creditors paid <30 days | 100% creditors paid <30 days | 100% creditors paid <30 days
26 |  | Implement approved capital infrastructure projects within budget and monitor expenditure against approved project allocations. | MFVM 13/FS/26/27 (IDP/TL) | Percentage capital infrastructure expenditure of approved projects. | 100% | 100% of approved capital infrastructure project budgets spent by 30 June 2027 |  | a) Capital project expenditure reports | N/A | 15% expenditure | 40% expenditure | 75% expenditure | 100% expenditure
Total Weighting
Revenue
27 | To improve revenue and all possible revenue streams applicable to KZN271 | Review financial policies | MFVM 14/FS/26/27 (IDP/TL) | Number of financial policies, strategies, Bylaws reviewed and approved by council | 15 | 15 financial policies, strategies, Bylaws reviewed and approved by council |  | a) Copy of the revised policies b) Copy of resolutions | N/A | N/A | N/A | N/A | Table reviewed policies, Strategies and Bylaw to council by 31 May 2027
28 |  | Enhance billing accuracy, strengthen debt management, and improve revenue collection mechanisms to maximise cash inflow. | MFVM 15/FS/26/27 (IDP/TL) | Percentage collection rate on current year billed revenue. | 95% | 95% Revenue collection rate as a percentage of billed amount per quarter up to 30 June 2027 |  | Revenue collection reports | N/A | 95% | 95% | 95% | 95%
29 |  | Strengthen credit control, debt collection processes, billing accuracy, and enforcement of revenue management policies. | MFVM 16/FS/26/27 (IDP/TL) | Percentage collection of historical debt and current billed revenue | NEW | 70% of historical debt collected/recovered by 30 June 2027 |  | a) Credit Control Reports b) Report on debt recovery campaign (Q2) |  | N/A | 20% collection of annual revenue target and initiation of debt recovery campaigns | 45% cumulative collection | 70% cumulative collection
30 |  | Generate billing reports | MFVM 17/FS/26/27 | Number of Billing reports generated | 12 | 12 Billing reports generated by 30 June 2027 |  | 12 Signed off Post Billing Reports from the financial system | N/A | 3 Monthly Billing reports generated (Jul, Aug, Sept) | 3 Monthly Billing reports generated (Oct, Nov, Dec) | 3 Monthly Billing reports generated (Jan, Feb, Mar) | 3 Monthly Billing reports generated (Apr, May, Jun)
Total Weighting
Supply Management
31 | To ensure the efficient, transparent and cost effective acquisition of goods, services for an organisation | Compiling and submission procurement plan to Provincial Treasury | MFVM 18/FS/26/27 (IDP/TL) | 2027/2028 Procurement Plan submitted to Provincial Treasury | 2026-06-30 | Submission of 2026/2027 Procurement Plan to Provincial Treasury by 30 June 2027 |  | a) 2027/2028 Procurement plan b) Proof of submission | N/A | N/A | N/A | N/A | Submission of 2027/2028 Procurement Plan to Provincial Treasury 30 June 2027
Total Weighting
Asset Management and Contract Management
32 | To develop and maintain systems and procedures for effective and sound management of municipal finances | Maintain an accurate, complete, and GRAP-compliant Fixed Asset Register (FAR) and submit periodic update reports to the Portfolio Committee for oversight. | MFVM 19/FS/26/27 | Number of quarterly reports on updated Asset Register in line with GRAP and Fixed Asset Register submitted to Portfolio Committee. | 4 | 4 reports on updated Asset Register in line with GRAP submitted to the Portfolio Committee (FAR) by 30 June 2027 |  | a) FAR reports b) Extract of portfolio minutes c) Annual FAR report and signed Asset register (Q4) | N/A | 1 GRAP-compliant FAR update report submitted (Q4) | 1 GRAP-compliant FAR update report submitted (Q1 report) | 1 GRAP-compliant FAR update report submitted (Q2 report) | 1 consolidated annual FAR report submitted
33 |  | Compile performance of service provider reports and submit to portfolio committee | MFVM 20/FS/26/27 | Number of monthly reports on Performance of service Providers compiled | 12 | 12 monthly reports on Performance of service Providers compiled by 30 June 2027 |  | a)Signed performance reports b) portfolio recommendations | N/A | 3 Monthly report on Performance of service providers(July ,August & September) | 3 Monthly report on Performance of service providers (Oct,Nov & Dec) | 3 Monthly report on Performance of service providers (Jan,Feb & March) | 3 Monthly report on Performance of service providers ( April, May & June)
To+A45:K48tal Weighting
Financial Management
34 | Compliance with financial legislation and policies | Prepare grant reconciliations | MFVM 21/FS/26/27 | Number of Grant reconciliations on all DORA reportable grants received to the Municipal Manager from National Treasury | 4 | 4 Grant reconciliations on all DORA reportable grants received to the Municipal Manager from National Treasury by 30 June 2027 |  | Grant reconciliation reports | N/A | 3 monthly Grant reconciliations (Jul, Aug, Sept) | 3 monthly Grant reconciliations (Oct, Nov, Dec) | 3 monthly Grant reconciliations (Jan, Feb, Mar) | 3 monthly Grant reconciliations (Apr, May, Jun)
35 | To ensure full compliance, effective utilisation, and accurate reporting of all DORA-allocated conditional grants in accordance with National Treasury requirements. | Strengthen grant governance, expenditure monitoring, reporting accuracy, and compliance with DORA, MFMA, and Treasury reporting frameworks. | MFVM 22/FS/26/27 (IDP/TL) | Percentage expenditure and compliance reporting of all DORA-reportable grants received | 100% | 100% expenditure and compliance reporting of all DORA-reportable grants received |  | a) DORA Grant Reports b) Grant registers c) Proof of submission |  | 20% expenditure and submission of Q1 DORA report | 45% cumulative expenditure and submission of Q2 DORA report | 75% cumulative expenditure and submission of Q3 DORA report | 100% expenditure and submission of Q4 DORA report
36 | To provide MANCO with accurate and reliable cash flow forecasts to support effective budget implementation and financial oversight. | Prepare, review, and submit accurate monthly cash flow forecast reports to MANCO | MFVM 23/FS/26/27 | Number of cashflow forecasts reports submitted to Manco | NEW | 4 cashflow forecasts reports submitted to Manco by 30 June 2027 |  | a) 4 cashflow forecasts reports b) Manco minutes / Extract | N/A | 1 cashflow forecast report submitted to Manco | 1 cashflow forecast report submitted to Manco | 1 cashflow forecast report submitted to Manco | 1 cashflow forecast report submitted to Manco
Total Weighting
Financial Ratios
37 | To measure municipality's operational efficiency, liquidity and stability | Calculation of ratio quarterly | MFVM 24/FS/26/27 (IDP/TL) | Ratio of months Cash/Cost coverage ratio | 3 months | 3 months cost coverage ratio per quarter up to 30 June 2026 |  | a) Report on Financial Performance Ratio | N/A | 3 months cost coverage ratio | 3 months cost coverage ratio | 3 months cost coverage ratio | 3 months cost coverage ratio
38 |  | Calculation of ratio quarterly | MFVM 25/FS/26/27 (IDP/TL) | Current ratio (current assets/current liabilities) | 1.5-2:1 | 2,1 a quarter up 30 June 2026 |  | a) Report on Financial Performance Ratio | N/A | 2.1 | 2.1 | 2.1 | 2.1
39 |  | Calculation of ratio quarterly | MFVM 26/FS/26/27 (IDP/TL) | Capital Expenditure Budget Implementation ratio | 95% | 95% |  | a) Report on Financial Performance Ratio | N/A | N/A | N/A | N/A | 95% expenditure
40 |  | Calculation of annually | MFVM 27/FS/26/27 (IDP/TL) | Percentage of budget for repairs and maintenance as a % of Property, Plants and Equipment and Investment Property (Carrying Value | 8% | 8% |  | a) Report on Financial Performance Ratio | N/A | N/A | N/A | N/A | 8%
41 |  | Calculation of annually | MFVM 28/FS/26/27 (IDP/TL) | Debt written off as % of provision for debt impairment | 100% | 3% |  | a) Report on Financial Performance Ratio | N/A | N/A | N/A | N/A | 3% of debt impairment raised.
Total Weighting
Financial reconciliations
42 | To develop and maintain systems and procedures for effective and sound management of municipal finances | Prepare monthly bank reconciliations | MFVM 29/FS/26/27 | Number of cash management reports submitted to Finance portfolio committee | 4 | 4 cash management reports submitted to Finance portfolio committee |  | a) cash management reports b) Finance portfolio extract | N/A | 1 cash management report submitted to Finance portfolio committee | 1 cash management report submitted to Finance portfolio committee | 1 cash management report submitted to Finance portfolio committee | 1 cash management report submitted to Finance portfolio committee
Total Weighting
Supplementary Valuation Roll
43 | To improve revenue and all possible revenue streams applicable to KZN271 | Maintenance of General V valuation Roll through Supplementary Valuation Roll | MFVM 30/FS/26/27 | Approved Supplementary Valuation Roll by Council | 2026-06-30 | Approved Supplementary Valuation Roll by Council by |  | (a) Certification by Municipal Valuer (b) Approved SVR (c) Council resolution | 1000000 | N/A | N/A | (a) Maintenance of General valuation Roll through Supplementary Valuation Roll by 31 March 2027 (b) Table draft SVR to council | (a) Table Supplementary consolidated Valuation Roll to Council for approval by 30 June 2027
Total Weighting
Signed off by: Chief Financial Officer
Date:
Signed by the Municipal Manager
Date:

## Sheet1
1 | sphe
2 | musa
3 | gugu
4 | fikile
5 | sne
6 | nomvelo
7 | bafana
8 | senzo
9 | senzo mhl
10 | khulani
11 | dominic
12 | nyako
13 | nondu
14 | xoli
15 | sthe
16 | lihle
17 | zama
18 | ntokozo